## Sheet1
CF LOGSHEET to WEB and DB to SQL
|  |  | Module | Feature | Status | Target Completion Date | Actual Completion Date
| 10 | 10% | Database | DB Design | Done | 2014-09-19 | 2014-09-19
|  |  |  | DB Initial Objects (Table) Creation | Done | 2014-09-22 | 2014-09-22
| 10 | 10% | Campaign | Campaign Web Page | Done | 2014-09-24 | 2014-09-24
|  |  |  | Add New Campaign | Done | 2014-09-24 | 2014-09-24
|  |  |  | Assign Campaign to Cycle | Done | 2014-09-24 | 2014-09-24
| 10 | 10% | Cycle | Cycle Web Page | Done | 2014-09-25 | 2014-09-25
|  |  |  | View Recent Cycle | Done | 2014-09-26 | 2014-09-26
|  |  |  | Add New Cycle | Done | 2014-09-26 | 2014-09-26
|  |  |  | Change Cycle Status | Done | 2014-10-03 | 2014-10-03
| 35 | 35% | Activity | Activity Web Page | Done | 2014-10-01
|  |  |  | Add Activity | Done | 2014-10-04
|  |  |  | Apply Validation on type of Time Usage base on Air Flow |  | 2014-10-17
|  |  |  | Apply Validation on type of Charging or non charging |  | 2014-10-10
|  |  |  | Apply Validation on type of Material Charge. |  | 2014-10-10
|  |  |  | Add CF Stage | Done | 2014-10-10 | 2014-10-09
|  |  |  | Input CF Tuyere | Done | 2014-10-03 | 2014-10-01
|  |  |  | User Interface Navigation |  | 2014-10-20
| 10 | 10% | Employee Shift | Employee Shift Web Page | Done | 2014-10-02 | 2014-10-08
|  |  |  | Add Employee Shift | Done | 2014-10-03 | 2014-10-08
| 15 | 15% | Reports | Reports Web Page |  | 2014-10-20
|  |  |  | Per Cycle Report |  | 2014-10-24
| 10 | 10% | Other Computations | Other CF Logsheet Computation |  | 2014-10-27
100%
Formulas:
Target Completion Date = [Actual Completion Date]